## Sheet1
Project Name: VoiceTotal Project Link: https://app.voicetotal.com/ SQA Engineer: Abdulla Al Bayzed Module: Signup, SignIn, SignOut, Flow, Team, Profile
Issue List for Total Voice
Date | Issue No | Issue Type | Status | Severity | Error Type | Module | Title | Description | Environments | Actual Result | Expected Result | Attachment | Remarks(Dev) | Remarks(SQA)
2025-06-03 | 1 | Bug | Solved | Major | Functional | Profile | [Profile Page] – Changes to First Name, Last Name, Phone, or Team Name in one account automatically reflect in other accounts | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Use two different account in different tab 3. Go to profile in one account 4. Change first name, last name, phone, company name 5. Pay attention to the other account profile | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | [Profile Page] – Changes to First Name, Last Name, Phone, or Team Name in one account automatically reflect in other accounts | Profile changes should only apply to the current user account | Attachment Link | Fixed | Fixed
2025-06-03 | 2 | Bug | Solved | Major | Functional | Flow (Forward Number) | [Flow Creation] – Forward number input only accepts numbers starting with +18, shows error for other valid country codes | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Click on the flow option 3. Fill up the required field 4. Write forward number without start +18 5. Click on create & pay attention to the page | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | [Flow Creation] – Forward number input only accepts numbers starting with +18, shows error for other valid country codes | The system should accept valid phone numbers with USA correct country code, not just +18 | Attachment Link | Fixed | Fixed
2025-06-03 | 3 | Enhancement | Solved | Enhancement | Functional | Assign Number | [Flow Creation] – "Assign Number" field does not display any numbers when clicked | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Click on flow option & create a flow 3. Click on the assign number field 4. Pay attention to this | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | [Flow Creation] – "Assign Number" field does not display any numbers when clicked | Assign Number field should be shown assigned or non assigned number | Attachment Link | Fixed | Fixed
2025-06-03 | 4 | Bug | Solved | Minor | GUI | Quick Links | [Team Member Account] – Quick links for "Create Flow", "Purchase Number", and "Team Member" are visible upon login | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Click on team & add a member 3. Log in into team member account 4. Pay attention to the dashboard | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | [Team Member Account] – Quick links for "Create Flow", "Purchase Number", and "Team Member" are visible upon login | Quick links should not be show in team member account | Attachment Link | Fixed | Fixed
2025-06-12 | 5 | Bug | Solved | Average | Functional | Team | In team member page displays previous admin's team members on first load after login another account | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Click on team & add a member 3. Logout from this account 4. Now login another account & Click team option 5. Pay attention to the team pages | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In team member page displays previous admin's team members on first load after login another account | Should display the current admin's team members after login | Attachment Link | Fixed | Fixed
2025-06-12 | 6 | Enhancement | Solved | Major | Functional | Billing | In account settings option add option to change payment card | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the billing & accounts 3. Pay attention to the both pages | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In account settings option add option to change payment card | User can update or replace the saved payment card from account settings | Attachment Link | Fixed | Fixed
2025-06-12 | 7 | Bug | Solved | Major | Functional | Accounts | In login allow account access without payment method added | Steps to Reproduce: 1. Signup into https://app.voicetotal.net/signup 2. Go to the payment method option but not payment 3. Now login into the account 4. Pay attention to the login process | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In login allow account access without payment method added | Login should not be allowed without set payment method | Attachment Link | Fixed | Fixed
2025-06-12 | 8 | Bug | Solved | Major | Functional | Team | In team member list added member disappears after some time | Steps to Reproduce: 1. Signup into https://app.voicetotal.net/signup 2. Go to the team and add a team member 3. Wait some time on this page and refresh the page 4. Pay attention to the team member list | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In team member list added member disappears after some time | Added team member should always be visible in the team member list unless intentionally removed | Attachment Link | Fixed | Fixed
2025-06-12 | 9 | Bug | Solved | Average | Functional | Profile | In profile section - sometimes low credit balance notification Blocks Entry Intermittently | Steps to Reproduce: 1. Login into https://app.voicetotal.net/signin 2. Click different section & also click on profile section 3. Pay attention to the profile section notifications | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In profile section - sometimes low credit balance notification Blocks Entry Intermittently | Profile should open without Low Credit Balance notification | Attachment Link | Fixed | Fixed
2025-06-12 | 10 | Bug | Solved | Major | Functional | Team | In team- deleted member cannot be added to another team | Steps to Reproduce: 1. Login into https://app.voicetotal.net/signin 2. Go to the team option and create one or more team member 3. Then delete team member 4. Add the deleted team member in another account 5. Pay attention to the team pages | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In team- deleted member cannot be added to another team | Deleted team member should be allowed to join another team | Attachment Link | Fixed | Fixed
2025-06-15 | 11 | Bug | Solved | Major | Functional | Password | In email sometimes password not shown when create a new account | Steps to Reproduce: 1. Signup to https://app.voicetotal.net/signup 2. Fill up required field and click submit 3. Pay attention to the email inbox | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In email sometimes password not shown when create a new account | Password should be shown in email inbox for new account create |  | Fixed | Fixed
2025-06-15 | 12 | Bug | Solved | Average | Functional | Auto-recharge | Auto-recharge is enabled by default after login with a newly created account | Steps to Reproduce: 1. Sign in to https://app.voicetotal.net/signin 2. Go to the billing section 3. Pay attention to the auto recharge section | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Auto-recharge is enabled by default after login with a newly created account | Auto-recharge should be disable for newly created account | Attachment Link | Fixed | Fixed
2025-06-16 | 13 | Bug | Solved | Major | Functional | Flow | Flow Call Pricing and Over Second Fields Accepting 0 Value During Flow Creation | Steps to Reproduce: 1. Sign in to https://app.voicetotal.net/signin 2. Click on the flow option & Click create flow 3. Fill up all the required field without call pricing & over seconds 4. Click create flow 5. Pay attention to the created flow | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Flow Call Pricing and Over Second Fields Accepting 0 Value During Flow Creation | Fields should not accept 0, must require a positive value | Attachment Link | Fixed | Fixed
2025-06-19 | 14 | Bug | Solved | Major | Functional | Credits | In credits show subscriptions package balance when create a new user account | Steps to Reproduce: 1. Signup to https://app.voicetotal.net/signup 2. Fill up all the required information for signup 3. Now Log in into the account 4. Pay attention to the credit balance | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In credits show subscriptions package balance when create a new user account | Credits should be show $ 0.00 for new user account | Attachment Link | Fixed | Fixed
2025-06-19 | 15 | Bug | Solved | Major | Functional | Billing | Manage Subscription functionality not working when cancelling subscription in Billing | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the billing section 3. Click on manage subscription & click cancel subscription 4. Pay attention to the cancel subscription process | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Manage Subscription functionality not working when cancelling subscription in Billing | Cancel subscription button should be work | Attachment Link | Fixed | Fixed
2025-06-19 | 16 | Bug | Solved | Average | Functional | Billing | In billing section auto recharge amount showing when logout & login in account | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the billing section 3. Select recharge amount & minimum credit threshold 4. Click on enable 5. Pay attention to the amount | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In billing section auto recharge amount showing when logout & login in account | Auto recharge amount should be shown without logout & login account | Attachment Link | Fixed | Fixed
2025-06-19 | 17 | Bug | Solved | Average | Functional | Billing(Invoice) | In billing section Invoice displays in HTML format instead of PDF when send in email | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the billing section 3. Click on invoice option 4. Click on Email, write the email address & send it 5. Pay attention to the email inbox & open the file | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In billing section Invoice displays in HTML format instead of PDF when send in email | Invoice should be rendered and sent in proper PDF format | Attachment LInk | Fixed | Fixed
2025-06-19 | 18 | Bug | Solved | Average | Functional | Team | Team creation allows phone number already used for main account | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the team section 3. Create a team using which number that used create main account 4. Pay attention to the team creation | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Team creation allows phone number already used for main account | Phone number used for the main account should not be accepted for team creation | Attachment Link | Fixed | Fixed
2025-06-19 | 19 | Bug | Solved | Minor | GUI | Numbers | Flow name dropdown scrolling not working when changing flow in Add Forward Number flow | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the number option 3. Click on '+' icon & click call flow dropdown list 4. Now scrolling it to see all list 5. Pay attention to the scrroling | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Flow name dropdown mouse scrolling not working when changing flow in Add Forward Number flow | Flow name dropdown should be mouse scroll properly | Attachment Link | Fixed | Fixed
2025-06-29 | 20 | Bug | Unresolved | Average | Functional | Team Member Account (Advance Filter) | Advanced Filter Not Working for Flow & Campaign in Team Member Account | Steps to Reproduce: 1. Log into a Team Member account 2. Go to https://app.voicetotal.net/signin 3. Click on Report option & click advance filter 4. Click on flow & campaign option 5. Pay attention to the working of flow & campaign | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Advanced Filter Not Working for Flow & Campaign in Team Member Account | Flow and Campaign should appear correctly when searched using the advanced filter | Attachment Link | Open | Open
2025-06-29 | 21 | Bug | Unresolved | Average | Functional | Report | "To" Date Not Displayed in Report Module When Searching with From & To Dates | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the report option & click date field 3. Insert from and to date 4. Pay attention to the searching result | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | "To" Date Not Displayed in Report Module When Searching with From & To Dates | "To" date should display correctly in search results | Attachment Link | Open | Open
2025-06-30 | 22 | Bug | Solved | Major | Functional | Billing | In billing section autorecharge in not enable by default when login new user account | Steps to Reproduce: 1. SignUp into https://app.voicetotal.net/signup 2. After signup log into the account 3. Go to the billing section 4. Pay attention to the auto recharge option | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In billing section autorecharge in not enable by default when login new user account | Autorecharge should be enable by default | Attachment Link | Fixed | Fixed
2025-06-30 | 23 | Bug | Unresolved | Average | Functional | Sign Up | Cancelled Subscription Email Cannot Be Used for New Account Sign-Up | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Fill up the required filled 3. Log into the account & go to billing section 4. Cancel the subscription 5. Now signup a new account using same email 6. Pay attention to the proceed to payment option | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Cancelled Subscription Email Cannot Be Used for New Account Sign-Up | Cancelled Subscription account email should be used for new account signup | Attachment Link | Open | Open
2025-06-30 | 24 | Bug | Solved | Major | Functional | Cancel Subscription | User Can Access Account if Logged in Within 30 Seconds After Subscription Cancellation | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Fill up the required filled 3. Log into the account & go to billing section 4. Cancel the subscription 5. Now login this account using same email 6. Pay attention to the login process | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | User Can Access Account if Logged in Within 30 Seconds After Subscription Cancellation | User access should be blocked immediately after subscription cancellation | Attachment Link | Fixed | Fixed
2025-06-30 | 25 | Bug | Solved | Average | Functional | Billing | Last 4 Digits of Card Number Not Displayed in Billing Section After Signup when signup with trial | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Fill up the required filled 3. Log into the account & go to billing section 4. Pay attention to the card number details | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Last 4 Digits of Card Number Not Displayed in Billing Section After Signup when signup with trial | Last 4 Digits of Card Number should be displayed | Attachment Link | Fixed | Fixed
2025-07-02 | 26 | Bug | Solved | Major | Functional | Auto-recharge | Creating Trial Account Triggers Two Identical Auto-Recharges Simultaneously | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Fill up the required filled 3. Log into the account & wait some times 4. Pay attention to the billing section | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Creating Trial Account Triggers Two Identical Auto-Recharges Simultaneously | Only one auto-recharge triggered on trial account creation | Attachment Link-1, Attachment-2 | Fixed | Fixed
2025-07-02 | 27 | Bug | Solved | Major | Functional | Auto-recharge | Auto-Recharge Activated in Billing After Signing Up with Trial Version | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Fill up the required filled 3. Log into the account 4. Pay attention to the billing section | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Auto-Recharge Activated in Billing After Signing Up with Trial Version | Auto-recharge should remain inactive for trial sign-up | Attachment Link | Fixed | Fixed
2025-07-03 | 28 | Bug | Unresolved | Minor | GUI | Email(Body) | In user email body text shown Total Voice instead of Voice Total when send any email | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Fill up the required filled 3. Log into the account 4. Pay attention to the email inbox | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In user email body text shown Total Voice instead of Voice Total when send any email | In Email body text should be show Voice Total | Attachment Link | Open | Open
2025-07-08 | 29 | Bug | Solved | Major | Functional | Accounts (Subscriptions) | Login Fails with 'Package Not Found' Error When Account Is Created Without Trial | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Fill up the required filled 3. Log into the account 4. Pay attention to the notifications | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Login Fails with 'Package Not Found' Error When Account Is Created Without Trial | User should log in successfully or see a clear message guiding them to activate a package | Attachment Link | Fixed | Fixed
2025-07-10 | 30 | Bug | Unresolved | Major | Functional | Reports | Weekly and Monthly Email Reports Not Being Sent | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the reports option 3. Open your account email inbox after one week or month 4. Pay attention to this | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Weekly and Monthly Email Reports Not Being Sent | Weekly and monthly email reports are sent automatically as scheduled | Attachment Link | Open | Open
2025-07-13 | 31 | Bug | Solved | Major | Functional | Sripe Account | In stripe account default card number not showing when create an account without trial period | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Select package & select without trial 3. Fill up stripe information 4. Create a account & log in into the stipe account 5. Pay attention to the default card number | Operating System: Windows 11 Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In stripe account default card number not showing when create an account without trial period | Default card number should be shown in stripe account | Attachment Link | Fixed | Fixed
2025-07-15 | 32 | Bug | Unresolved | Average | Functional | Reports | In summary and reports revenue data is not same when filtering | Steps to Reproduce: 1. Log into https://app.voicetotal.net/signin 2. Go to the reports option 3. Click on date field both summary & reports 4. Set a date for checking 5. Pay attention to the total revenue | Operating System: Windows 11 Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In summary and reports revenue data is not same when filtering | Summary & reports revenue should be same | Attachment Link | Open | Open
2025-07-21 | 33 | Bug | Unresolved | Average | GUI | Email(Body) | In email(body) is not show account status trial when create account with trial | Steps to Reproduce: 1. For signup go to https://app.voicetotal.net/signup 2. Select package & select without trial 3. Fill up stripe information 4. Go to the admin email account 5. Pay attention to the email body | Operating System: Windows 11 Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In email(body) is not show account status trial when create account with trial | Email body should be show account status trial when create account with trial | Attachment Link | Open | Open
2025-07-22 | 34 | Bug | Unresolved | Average | Functional | Superadmin(Users) | In users team is not shown when log into superadmin | Steps to Reproduce: 1. Log into as a Superadmin https://app.voicetotal.net/signin 2. Go to the Users 3. Click any team member eye icon 4. Pay attention to this no team shown | Operating System: Windows 11 Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In users team is not shown when log into superadmin | "Users' team should be displayed in the Super Admin panel | Attachment-1, Attachment-2 | Open | Open
2025-07-22 | 35 | Bug | Unresolved | Minor | GUI | Superadmin(Dashboard) | In Superadmin panel is shown credit balance when log in as a superadmin | Steps to Reproduce: 1. Log into as a Superadmin https://app.voicetotal.net/signin 2. Pay attention to the left side bottom | Operating System: Windows 11 Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In Superadmin panel is shown credit balance when log in as a superadmin | Credit balance should not shown in Superadmin | Attachment Link | Open | Open
2025-07-22 | 36 | Bug | Unresolved | Average | GUI | Superadmin(Packages) | In Superadmin packages show only 1 active user instead of all active users | Steps to Reproduce: 1. Log into as a Superadmin https://app.voicetotal.net/signin 2. Go to the packages and see the active packages | Operating System: Windows 11 Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In Superadmin packages show only 1 active user instead of all active users | All active users should be shown in superadmin packages | Attachment Link | Open | Open